Procurement Management Plan

Mumbai–Ahmedabad High-Speed Rail Corridor – Timetable Optimization System

1. Introduction

1.1 Project Overview

The Mumbai–Ahmedabad High-Speed Rail Corridor aims to enhance rail operations through an AI-driven timetable optimization system. The project will develop an advanced scheduling solution that integrates predictive analytics, real-time adjustments, and compliance with railway standards.

1.2 Purpose of the Procurement Management Plan

This plan ensures that all procurement activities align with project goals, are cost-effective, and meet quality standards. It provides a structured approach for acquiring essential resources while mitigating risks.

2. Procurement Management Approach

2.1 Procurement Integration with Project Planning

Procurement activities are aligned with the project schedule, ensuring that key components are available as needed. The procurement process integrates with:

- Work Breakdown Structure (WBS) – to determine procurement dependencies.

- Project Schedule – to align procurement with implementation milestones.

- Risk Management Plan – to mitigate procurement risks such as delays or non-compliance.

2.2 Coordination with Project Stakeholders

Procurement is managed collaboratively with NHSRCL, technical teams, and vendors to ensure seamless integration into existing infrastructure.

3. Procurement Process

3.1 Identifying Procurement Needs

The High-Performance Cloud Server is critical for supporting real-time AI computations. The procurement process includes:

- Identifying technical specifications.

- Analyzing compatibility with existing NHSRCL IT infrastructure.

- Ensuring vendor compliance with Indian railway cybersecurity regulations.

3.2 Make-or-Buy Analysis

| Item | Make Decision | Buy Decision |
| --- | --- | --- |
| AI-driven Scheduling Software | Internal development (Project team) | – |
| Cloud-based High-Performance Server | – | Procured from external vendors |
| Data Integration APIs | Developed in-house | – |

The High-Performance Cloud Server will be procured externally to ensure reliability and compliance.

4. Procurement Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Project Manager (Roger Candoo) | Approves procurement requests, oversees procurement timeline |
| Procurement Lead | Manages vendor selection and contract negotiations |
| Technical Lead | Ensures compatibility with project requirements |
| Quality Assurance Lead | Conducts compliance and performance evaluations |
| Finance Team | Manages procurement budgeting and approvals |

5. Procurement Requirements

5.1 High-Performance Cloud Server Specifications

- Processor: Minimum 32-core CPU (AMD EPYC or Intel Xeon)

- RAM: 256 GB minimum

- Storage: 2 TB SSD + scalable cloud storage

- Network: 10 Gbps bandwidth for real-time data processing

- Security: Compliance with Indian data protection laws

- Uptime: 99.99% availability

5.2 Quality Requirements

- Must support real-time AI-based schedule adjustments.

- Integration with existing NHSRCL railway control systems.

- Data encryption and secure API connectivity.

6. Vendor Management

6.1 Vendor Selection Criteria

- Proven experience in providing cloud infrastructure for railway or government projects.

- Compliance with ISO 27001 and Indian IT Act.

- Minimum 99.99% server uptime guarantee.

- Established local support team in India.

6.2 Vendor Evaluation Process

- Shortlisting: Identify at least three vendors.

- Technical Review: Validate compliance with NHSRCL requirements.

- Financial Review: Assess total cost of ownership (TCO) and service-level agreements (SLAs).

- Final Selection: Conduct negotiations and sign a contract.

7. Procurement Documentation

7.1 Types of Procurement Documents

- Request for Proposal (RFP) – Details technical and quality requirements.

- Request for Quotation (RFQ) – Requests pricing and availability from vendors.

- Service Level Agreement (SLA) – Defines uptime, support, and maintenance terms.

7.2 Bid Document Preparation and Submission

- The RFP will be issued by 15th March 2025.

- Vendors must submit proposals by 30th March 2025.

- Evaluation and final selection by 15th April 2025.

8. Evaluation Criteria

| Category | Weight (%) | Details |
| --- | --- | --- |
| Technical Compliance | 40% | Adherence to NHSRCL requirements, performance benchmarks |
| Cost | 30% | Competitive pricing, total cost of ownership |
| Vendor Reputation | 20% | Proven track record in similar projects |
| Support & Maintenance | 10% | Availability of 24/7 technical support |

9. Contract Management

9.1 Finalizing Contracts

- The contract will be awarded by 20th April 2025.

- Legal compliance with Indian Contract Act, 1872.

- Payments in Indian Rupees (INR), milestone-based.

9.2 Risk Management in Contracts

| Risk | Mitigation Strategy |
| --- | --- |
| Vendor fails to deliver on time | Include penalties for delays |
| Performance issues | Include a service refund clause |
| Non-compliance with regulations | Require compliance certificates before final payment |

10. Procurement Metrics

| Metric | Target |
| --- | --- |
| Procurement timeline adherence | 100% compliance with schedule |
| Vendor compliance rate | 100% adherence to requirements |
| Cost variance | <5% deviation from budget |
| Uptime performance | Minimum 99.99% |

11. Constraints and Assumptions

11.1 Constraints

- Budget Limit: Procurement must fit within project financial constraints.

- Regulatory Approval: NHSRCL must approve vendor selection.

- Time Sensitivity: Any delays may impact the AI system development.

11.2 Assumptions

- Vendors will provide support for at least 5 years.

- Data security regulations will not significantly change within 3 years.

12. Procurement Risk Management

| Risk | Impact | Mitigation Strategy |
| --- | --- | --- |
| Supply Chain Delays | High | Identify multiple suppliers |
| Cost Overruns | Medium | Negotiate fixed-price contracts |
| Quality Issues | High | Implement acceptance testing |
| Vendor Non-Compliance | Medium | Require regulatory certifications upfront |

13. Procurement Closeout

13.1 Procurement Closure Activities

- Verify all contract deliverables are met.

- Conduct final performance audit on procured server.

- Obtain NHSRCL sign-off on procurement completion.

- Archive all procurement documents for audit compliance.

13.2 Lessons Learned

- Document key insights from the procurement process.

- Identify best practices for future railway projects.

- Improve vendor management for subsequent procurements.