## Stakeholder Register
Name | Role | Contact | Department | Influence | Interest | Communication_Preference | Engagement_Strategy
Michael Chen | Project Sponsor / CTO | michael.chen@company.com | Technology | High | High | Weekly executive reports | Manage closely - key decision maker
Lisa Rodriguez | Business Owner / VP E-Commerce | lisa.rodriguez@company.com | Business | High | High | Bi-weekly business reviews | Manage closely - business requirements owner
Sarah Johnson | Project Manager | sarah.johnson@company.com | PMO | High | High | Daily standups, weekly reports | Manage closely - project execution
David Kim | Technical Lead / Senior Architect | david.kim@company.com | Technology | High | High | Daily standups, technical reviews | Manage closely - technical decisions
Jennifer Wu | QA Lead | jennifer.wu@company.com | Quality Assurance | Medium | High | Weekly QA reports | Keep satisfied - quality assurance
Robert Taylor | Security Lead / Information Security Officer | robert.taylor@company.com | Information Security | Medium | High | Monthly security reviews | Keep satisfied - security compliance
Alex Chen | Senior Developer | alex.chen@company.com | Development | Medium | High | Daily standups | Keep informed - development progress
Maria Garcia | Senior Developer | maria.garcia@company.com | Development | Medium | High | Daily standups | Keep informed - development progress
James Wilson | Frontend Developer | james.wilson@company.com | Development | Low | High | Daily standups | Keep informed - development progress
Emily Davis | Frontend Developer | emily.davis@company.com | Development | Low | High | Daily standups | Keep informed - development progress
Kevin Park | DevOps Engineer | kevin.park@company.com | Operations | Medium | Medium | Weekly ops reviews | Keep satisfied - infrastructure support
Rachel Kim | Business Analyst | rachel.kim@company.com | Business Analysis | Medium | High | Weekly requirements reviews | Keep satisfied - requirements clarity
Sophie Turner | UX Designer | sophie.turner@company.com | Design | Medium | High | Design reviews, user feedback sessions | Keep satisfied - user experience
Tom Anderson | QA Engineer | tom.anderson@company.com | Quality Assurance | Low | Medium | Weekly QA reports | Keep informed - testing progress
John Smith | Customer Representative | john.smith@customer.com | Customer | High | High | Monthly customer updates | Manage closely - customer satisfaction
Jane Doe | End User Representative | jane.doe@customer.com | Customer | Medium | High | User testing sessions | Keep satisfied - user acceptance
Mark Thompson | Infrastructure Manager | mark.thompson@company.com | Infrastructure | Medium | Medium | Monthly infrastructure reviews | Keep satisfied - infrastructure support
Anna Lee | Compliance Officer | anna.lee@company.com | Legal/Compliance | Medium | Medium | Quarterly compliance reviews | Keep informed - compliance requirements