## Tabelle1
Risk ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score (P x I) | Response Strategy | Owner | Monitoring Frequency
T-001 | AI model fails in 10%+ of tests | Technical | 4 | 5 | 20 | Implement secondary validation algorithm | Technical Lead | Weekly
T-002 | NHSRCL delays approval by 30+ days | Operational | 3 | 4 | 12 | Weekly NHSRCL progress meetings | Stakeholder Engagement Specialist | Bi-weekly
T-003 | Budget overrun > 10% | Financial | 4 | 5 | 20 | "Reduce non-critical features reallocate budget" | Project Manager | Monthly
T-004 | Regulatory non-compliance leading to fines | Regulatory | 2 | 3 | 6 | Conduct compliance audit at project phases | Compliance Officer | Quarterly
O-001 | AI model exceeds performance expectations | Technical | 2 | 4 | 8 | "Reduce manual schedule reviews automate further" | Technical Lead | Monthly
O-002 | NHSRCL fast-tracks approval | Operational | 3 | 4 | 12 | "Accelerate project schedule reduce contingency reserve" | Stakeholder Engagement Specialist | Bi-weekly
O-003 | Early AI validation reduces rework costs | Financial | 3 | 4 | 12 | Shift savings to additional performance enhancements | Project Manager | Quarterly