## Tabelle1
Risk ID | Risk Category | Risk Description | Likelihood (L) | Impact (I) | Risk Score (LxI) | Mitigation Strategy | Risk Owner | Residual Risk
R1 | Requirements Management | Requirement misalignment due to unclear or incomplete requirements from NHSRCL. | 3 | 4 | 12 | Frequent communication and validation checkpoints with NHSRCL. | Project Manager | Medium
R2 | Financial | Budget constraints leading to insufficient funding for project execution. | 4 | 5 | 20 | Provide multiple cost-efficient options and alternative funding sources. | Finance Team | High
R3 | Regulatory Compliance | Non-compliance with railway standards and regulations. | 3 | 4 | 12 | Engage compliance experts early to ensure regulatory alignment. | Regulatory Compliance Team | Medium
R4 | Technology | Failures in AI/ML-driven scheduling optimization leading to inefficiencies. | 2 | 3 | 6 | Develop a fallback plan using traditional scheduling methods. | Technical Development Team | Low
R5 | Stakeholder Management | Resistance from NHSRCL staff and stakeholders to adopt new scheduling systems. | 4 | 4 | 16 | Implement a stakeholder engagement and training program. | Change Management Team | Medium
R6 | Operational | Unforeseen operational disruptions such as extreme weather or infrastructure failures. | 3 | 5 | 15 | Develop contingency plans for operational disruptions. | Operations Team | High
R7 | Project Execution | Delays in project milestones due to dependencies on multiple teams and external factors. | 3 | 4 | 12 | Adopt an agile project management approach with regular progress reviews. | Project Execution Team | Medium
R8 | Security & Data Integrity | Data inaccuracies or breaches affecting the reliability of scheduling data. | 2 | 4 | 8 | "Implement robust encryption | authentication | and data validation mechanisms."
IT Security Team | Medium